## Level 3_Bronze
Project Plan for Geriatric Emergency Department Accreditation (GEDA) - Level 3 (Bronze)
https://www.acep.org/globalassets/sites/geda/documnets/GEDA-criteria.pdf
Accredited Geriatric EDs will provide a clearly defined set of measurable criteria, standardized to improve quality of emergency care for older adults. A Geriatric ED is not a separate space, but is a general ED that has made the decision to intentionally implement changes in its people, processes and place in order to improve the quality of care provided to older adults. Level 3 (Bronze) accreditation means that the ED practices one or more geriatric-specific initiatives that are reasonably expected to elevate the level of elder care provided in one or more specific areas. Personnel to implement these efforts are identified and trained. Metrics for the initiative/initiatives are followed.
GEDA Criteria - Level 3 (Bronze) | Targeted Due Date (if planning to be accredited by 12/31/23) | Responsible Party | Status
Prepare for Accreditation
Review GEDA Criteria and Guidelines as posted on the American College of Emergency Physicians' website: https://www.acep.org/geda/ |  |  | Not Started
a) Staffing
Identify 1 MD or DO with evidence of 4 hours of focused education for geriatric EM The institution should ensure availability of at least one EM Boarded, MD/DO on staff who can provide evidence of some focused emergency department physician education specifically relevant to the provision of emergency care of older people. |  |  | Not Started
Identify 1 RN with evidence of focused education for geriatric EM The institution should ensure availability of at least one RN on staff who can provide evidence of some focused emergency nursing education specifically relevant to the provision of emergency care of older people. |  |  | Not Started
b) Education
Physician Champion/Medical Director & RN Champion attend HANYS Geriatric ED Bootcamp Although not required for accreditation, it is strongly encouraged that at least the Physician Champion and RN Champion attend Bootcamp. Continuing education credits will be offered, that will count toward the GEDA Criteria for Education. This training will position your ED for success with achieving GEDA accreditation. Other members of the Geriatric ED are also welcome to attend this virtual training event. |  |  | Not Started
Staff physician education (hours) related to 8 domains of GEM - 4 hours for Physician Champion/Medical Directors This training requirement must be demonstrated through coursework: 1) focused on geriatric specific syndromes and concepts (e.g., atypical presentation of disease, changes with age, transitions of care) relevant to emergency medicine, 2) focused on clinical issues nearly exclusive to geriatric ED patients (e.g., end of life care, dementia, delirium, systems of care for older adults), or 3) discussing issues common to all ED patients but focused on the unique factors found in older adults (e.g., trauma in older adults, cardiac arrest care for the geriatric patient.) For physician champion / medical directors applying to lead Level 3 Geriatric EDs, 4 hours of education are required for the initial certification and for each renewal. These educational requirements may be demonstrated through appropriate geriatric-focused CME with completion certificate. |  |  | Not Started
Nursing education in geriatric emergency care A department should document its nursing educational activity and submit the documentation for consideration. Some examples: a. GENE course from Emergency Nurses Association https://www.ena.org/education/education/GENE/Pages/default.aspx b. Emergency Department nursing modules from NICHE http://www.nicheprogram.org/knowledgecenter/webinars/archived-webinars/ c. Locally developed nursing education modules |  |  | Not Started
c) Policies/Protocols, Guidelines and Procedures
Provide evidence of at least one geriatric-specific emergency care initiative (e.g. elder mistreatment, cognitive impairment, or other policies/ protocols / procedures.) Protocol should specifically address the emergency care needs of older adults. These protocols or procedures should describe the process through which this care improvement activity takes place for older patients while in the ED and how it is tracked with regards to adherence and care (i.e., who does the process, on whom the process is done, and how the process is triggered, etc.) This description should be detailed enough for the reviewers to understand how it is implemented, including information about staff education, how it is integrated into workflow, and strategies for tracking implementation. These protocols or procedures should describe the process through which a care improvement activity takes place for older patients while in the ED and how it is tracked with regards to adherence and improvement (i.e., who does the process, on whom the process is done, and how the process is triggered, etc.) It is not sufficient to describe an already existent hospital-wide policy that just happens to include the ED or an already existent ED policy that just happens to include older patients. |  |  | Not Started
Provide evidence of a Urinary Catheter Minimization policy/procedure/protocol. ACEP/GEDA believes this policy/procedure/protocol represents standard of care and became baseline for all Geriatric Emergency Departments beginning in 2023. | N/A if Submitting Prior to July, 2023 | N/A if Submitting Prior to July, 2023 | Not Started
Provide evidence of an NPO Status Minimization policy/procedure/protocol. ACEP/GEDA believes this policy/procedure/protocol represents standard of care and became baseline for all Geriatric Emergency Departments beginning in 2023. | N/A if Submitting Prior to July, 2023 | N/A if Submitting Prior to July, 2023 | Not Started
Provide evidence of a Physical Restraint Use policy/procedure/protocol. ACEP/GEDA believes this policy/procedure/protocol represents standard of care and became baseline for all Geriatric Emergency Departments beginning in 2023. | N/A if Submitting Prior to July, 2023 | N/A if Submitting Prior to July, 2023 | Not Started
d) Quality Improvement
Level 3s do not need an official QI program from their Geriatric EDs, however, implementation tracking (including adherence and improvement) is required. A description of how the ED is ensuring that the program instituted is implemented and adhered to is sufficient. It is anticipated that adherence may not be 100%, especially at first, but there must be a plan to track the implementation and an expectation of aiming towards continued improvement in adherence. (For example, monthly chart review of modest number of random charts, or EHR data tracking of patients of interest, etc. It should be clearly explained who is expected to receive the intervention - denominator- and how you will know if the intervention was done - numerator.) |  |  | Not Started
e) Outcome Measures - N/A for Level 3 (Bronze)
f) Equipment and Supplies
Access to, and pictorial evidence of mobility aids (4-point walkers, canes) for 24/7 use in the ED. |  |  | Not Started
g) Physical Environment
Easy access to, and pictorial evidence of free food and drink, 24 hours a day. |  |  | Not Started
Submission of Application for Accreditation
Create a login and complete application via online application portal on the American College of Emergency Physicians' website: https://www.acep.org/geda/ Level 3 applicants will be notified of decision within 16 to 18 weeks after online application is submitted. |  |  | Not Started
Submit application fee of $ 2,500 to the American College of Emergency Physicians via instructions on the ACEP portal. Request ACEP "discount code" from HANYS if eligible for a scholarship so the $ 2,500 application fees will be waived. |  |  | Not Started

## Level 2_Silver
Project Plan for Geriatric Emergency Department Accreditation (GEDA) - Level 2 (Silver)
https://www.acep.org/globalassets/sites/geda/documnets/GEDA-criteria.pdf
Accredited Geriatric EDs will provide a clearly defined set of measurable criteria, standardized to improve quality of emergency care for older adults. A Geriatric ED is not a separate space, but is a general ED that has made the decision to intentionally implement changes in its people, processes and place in order to improve the quality of care provided to older adults. Level 2 (Silver) accreditation means that the ED has integrated and sustained initiatives for the care of older adults into daily operations. It demonstrates interdisciplinary cooperation for delivery of age friendly services under an established supervisor or director to coordinate the staff who perform these services.
GEDA Criteria - Level 2 (Silver) | Targeted Due Date (if planning to be accredited by 12/31/23) | Responsible Party | Status
Prepare for Accreditation
Review GEDA Criteria and Guidelines as posted on the American College of Emergency Physicians' website: https://www.acep.org/geda/ |  |  | Not Started
a) Staffing
Identify 1 MD or DO with evidence of 6 hours of focused education for geriatric EM The institution should ensure availability of at least one EM Boarded, MD/DO on staff who can provide evidence of some focused emergency department physician education specifically relevant to the provision of emergency care of older people. |  |  | Not Started
Identify 1 RN with evidence of focused education for geriatric EM The institution should ensure availability of at least one RN on staff who can provide evidence of some focused emergency nursing education specifically relevant to the provision of emergency care of older people. |  |  | Not Started
Identify Physician Champion / Medical Director The institution should provide an EM Boarded emergency physician ‘champion’ or medical director who possesses expertise specifically relevant to the provision of emergency care of older people with the following responsibilities: a. to act as Geriatric EM educational leader/coordinator for EM providers across multiple disciplines b. to Oversee GED operations including: i. Implementation and regular assessment of protocol and policy guidelines of geriatricspecific initiatives ii. Coordination/guidance of GED staff workflow iii. Coordination of interdisciplinary team workflow in the GED c. to act as the Quality improvement team leader overseeing adherence to geriatric-specific protocols d. to develop and oversee outcome measures documentation including specific GED process and outcome metrics e. to act as Coordinator for maintenance of GED environment (i.e., specific equipment and supplies) f. to Liaison between hospital leadership and the GED g. to act as Quality assurance team leader for geriatric patient case reviews/complaints h. to Coordinator of GEM research initiatives (if applicable) |  |  | Not Started
Identify nurse case manager/transitional care nurse present > 56 hrs/week The institution should provide an identified nurse case manager or transitional care nurse or equivalent who should be present in the ED for at least 56 hours/week of clinical coverage. This nurse case manager or social worker shall have responsibility for complex geriatric patient care and responsibility for geriatric patient capacity development/performance improvement within the ED. |  |  | Not Started
Establish an interdisciplinary geriatric assessment team includes at least 2 additional roles The institution should ensure availability of an Inter-disciplinary geriatric assessment team, including at least 2 of the following roles available to the ED: Physiotherapy, occupational therapy, social work, or medication management |  |  | Not Started
b) Education
Physician Champion/Medical Director & RN Champion attend HANYS Geriatric ED Bootcamp Although not required for accreditation, it is strongly encouraged that at least the Physician Champion and RN Champion attend Bootcamp. Continuing education credits will be offered, that will count toward the GEDA Criteria for Education. This training will position your ED for success with achieving GEDA accreditation. Other members of the Geriatric ED are also welcome to attend this virtual training event. |  |  | Not Started
Staff physician education (hours) related to 8 domains of GEM - 6 hours for Physician Champion/Medical Directors This training requirement must be demonstrated through coursework: 1) focused on geriatric specific syndromes and concepts (e.g., atypical presentation of disease, changes with age, transitions of care) relevant to emergency medicine, 2) focused on clinical issues nearly exclusive to geriatric ED patients (e.g., end of life care, dementia, delirium, systems of care for older adults), or 3) discussing issues common to all ED patients but focused on the unique factors found in older adults (e.g., trauma in older adults, cardiac arrest care for the geriatric patient.) For physician champion / medical directors applying to lead Level 3 Geriatric EDs, 4 hours of education are required for the initial certification and for each renewal. These educational requirements may be demonstrated through appropriate geriatric-focused CME with completion certificate. |  |  | Not Started
Nursing education in geriatric emergency care A department should document its nursing educational activity and submit the documentation for consideration. Some examples: a. GENE course from Emergency Nurses Association https://www.ena.org/education/education/GENE/Pages/default.aspx b. Emergency Department nursing modules from NICHE http://www.nicheprogram.org/knowledgecenter/webinars/archived-webinars/ c. Locally developed nursing education modules |  |  | Not Started
c) Policies/Protocols, Guidelines and Procedures
Provide evidence of at least one geriatric-specific emergency care initiative (e.g. elder mistreatment, cognitive impairment, or other policies/ protocols / procedures.) Protocol should specifically address the emergency care needs of older adults. These protocols or procedures should describe the process through which this care improvement activity takes place for older patients while in the ED and how it is tracked with regards to adherence and care (i.e., who does the process, on whom the process is done, and how the process is triggered, etc.) This description should be detailed enough for the reviewers to understand how it is implemented, including information about staff education, how it is integrated into workflow, and strategies for tracking implementation. These protocols or procedures should describe the process through which a care improvement activity takes place for older patients while in the ED and how it is tracked with regards to adherence and improvement (i.e., who does the process, on whom the process is done, and how the process is triggered, etc.) It is not sufficient to describe an already existent hospital-wide policy that just happens to include the ED or an already existent ED policy that just happens to include older patients. |  |  | Not Started
Provide evidence of a Urinary Catheter Minimization policy/procedure/protocol. ACEP/GEDA believes this policy/procedure/protocol represents standard of care and became baseline for all Geriatric Emergency Departments beginning in 2023. | N/A if Submitting Prior to July, 2023 | N/A if Submitting Prior to July, 2023 | Not Started
Provide evidence of an NPO Status Minimization policy/procedure/protocol. ACEP/GEDA believes this policy/procedure/protocol represents standard of care and became baseline for all Geriatric Emergency Departments beginning in 2023. | N/A if Submitting Prior to July, 2023 | N/A if Submitting Prior to July, 2023 | Not Started
Provide evidence of a Physical Restraint Use policy/procedure/protocol. ACEP/GEDA believes this policy/procedure/protocol represents standard of care and became baseline for all Geriatric Emergency Departments beginning in 2023. | N/A if Submitting Prior to July, 2023 | N/A if Submitting Prior to July, 2023 | Not Started
Documentation of implementation of at least 10 items (prior to July, 2023) or 7 items (if submitting after July, 2023) from the ED Model of Care for patients over 65 yrs These protocols or procedures should describe the process through which this care improvement activity takes place for older patients while in the ED and how it is tracked with regards to adherence and care (i.e., who does the process, on whom the process is done, and how the process is triggered, etc.) A patient’s eligibility for GED initiatives may vary across intervention type and institution. For example, eligibility may be based on age, screening tool results, or prior ED history. While ACEP will accept a range of definitions of patient eligibility, you should specify how you are defining eligibility for the purposes of measuring adherence (i.e., the denominator) for each criterion being evaluated. See https://www.acep.org/globalassets/sites/geda/documnets/edmodelofcarelist.pdf for details about the ED Model of Care. |  |  | Not Started
d) Quality Improvement
Adherence to 3 baseline protocols (urinary catheter minimization, NPO status minimization and physical restraint use) plus the 7 optional components chosen in the Policies, Guidelines and Procedures section based on random chart audit There should be evidence of efforts to ensure effective and appropriate utilization of above policies and guidelines with adherence to the 10 components chosen in “Policies guidelines and procedures”. |  |  | Not Started
e) Outcome Measures
Track at least 3 process and outcome metrics for eligible patients for at least 3 items from the ED Model of Care. See https://www.acep.org/globalassets/sites/geda/documnets/outcomemeasureslist.pdf for details about acceptable measures. The ED should track both process and outcomes metrics related to eligible GED patients. These should include demonstration of process and outcome metrics in the majority of eligible GED patients in at least 3 metrics for at least 3 of the policies/ protocols guidelines or procedures chosen from the ED Model of Care (see Policies/Protocols, Guidelines and Processes section above). |  |  | Not Started
f) Equipment and Supplies
Access to, and pictorial evidence of mobility aids (4-point walkers, canes) for 24/7 use in the ED. |  |  | Not Started
Access to, and pictorial evidence of access to at least 3 additional supplies (see list below) for 24/7 use in the ED. - Non--slip socks - Pressure--ulcer reducing mattresses and pillows - Blanket warmer - Hearing assist devices - Bedside commodes - Condom catheters - Low beds - Reclinable arm chairs |  |  | Not Started
g) Physical Environment
Easy access to, and pictorial evidence of free food and drink, 24 hours a day. |  |  | Not Started
Two chairs per patient bed to promote visitors and the possibility of sitting, and pictorial evidence thereof. |  |  | Not Started
A large-face analog clock in each GED patient room, and pictorial evidence thereof. |  |  | Not Started
Submission of Application for Accreditation
Create a login and complete application via online application portal on the American College of Emergency Physicians' website: https://www.acep.org/geda/ Level 2 applicants will be notified of decision within 16 to 18 weeks after online application is submitted. |  |  | Not Started
Submit application fee of $ 7,500 to the American College of Emergency Physicians via instructions on the ACEP portal. |  |  | Not Started
ACEP will assign a reviewer for a discretionary Level 2 site visit and/or required phone conversation post application. |  |  | Not Started

## Level 1_Gold
Project Plan for Geriatric Emergency Department Accreditation (GEDA) - Level 1 (Gold)
https://www.acep.org/globalassets/sites/geda/documnets/GEDA-criteria.pdf
Accredited Geriatric EDs will provide a clearly defined set of measurable criteria, standardized to improve quality of emergency care for older adults. A Geriatric ED is not a separate space, but is a general ED that has made the decision to intentionally implement changes in its people, processes and place in order to improve the quality of care provided to older adults. Level 1 (Gold) accreditation means that the ED has policies, guidelines, procedures, and staff (both within the ED and throughout the institution) providing a coherent system of care targeting and measuring specific ED outcomes for older adults that form an overall elevation in ED operations and transitions of care both to and from the ED, all coordinated for the improved care of older adults. Additionally identified physical plant enhancements targeted to improve older adult care can exist.
GEDA Criteria - Level 1 (Gold) | Targeted Due Date (if planning to be accredited by 12/31/23) | Responsible Party | Status
Prepare for Accreditation
Review GEDA Criteria and Guidelines as posted on the American College of Emergency Physicians' website: https://www.acep.org/geda/ |  |  | Not Started
a) Staffing
Identify 1 MD or DO with evidence of 6 hours of focused education for geriatric EM The institution should ensure availability of at least one EM Boarded, MD/DO on staff who can provide evidence of some focused emergency department physician education specifically relevant to the provision of emergency care of older people. |  |  | Not Started
Identify 1 RN with evidence of focused education for geriatric EM The institution should ensure availability of at least one RN on staff who can provide evidence of some focused emergency nursing education specifically relevant to the provision of emergency care of older people. |  |  | Not Started
Identify Physician Champion / Medical Director The institution should provide an EM Boarded emergency physician ‘champion’ or medical director who possesses expertise specifically relevant to the provision of emergency care of older people with the following responsibilities: a. to act as Geriatric EM educational leader/coordinator for EM providers across multiple disciplines b. to Oversee GED operations including: i. Implementation and regular assessment of protocol and policy guidelines of geriatricspecific initiatives ii. Coordination/guidance of GED staff workflow iii. Coordination of interdisciplinary team workflow in the GED c. to act as the Quality improvement team leader overseeing adherence to geriatric-specific protocols d. to develop and oversee outcome measures documentation including specific GED process and outcome metrics e. to act as Coordinator for maintenance of GED environment (i.e., specific equipment and supplies) f. to Liaison between hospital leadership and the GED g. to act as Quality assurance team leader for geriatric patient case reviews/complaints h. to Coordinator of GEM research initiatives (if applicable) |  |  | Not Started
Identify nurse case manager/transitional care nurse present > 56 hrs/week The institution should provide an identified nurse case manager or transitional care nurse or equivalent who should be present in the ED for at least 56 hours/week of clinical coverage. This nurse case manager or social worker shall have responsibility for complex geriatric patient care and responsibility for geriatric patient capacity development/performance improvement within the ED. |  |  | Not Started
Establish an interdisciplinary geriatric assessment team includes at least 2 additional roles The institution should ensure availability of an Inter-disciplinary geriatric assessment team, including at least 2 of the following roles available to the ED: Physiotherapy, occupational therapy, social work, or medication management |  |  | Not Started
b) Education
Physician Champion/Medical Director & RN Champion attend HANYS Geriatric ED Bootcamp Although not required for accreditation, it is strongly encouraged that at least the Physician Champion and RN Champion attend Bootcamp. Continuing education credits will be offered, that will count toward the GEDA Criteria for Education. This training will position your ED for success with achieving GEDA accreditation. Other members of the Geriatric ED are also welcome to attend this virtual training event. |  |  | Not Started
Staff physician education (hours) related to 8 domains of GEM - 6 hours for Physician Champion/Medical Directors This training requirement must be demonstrated through coursework: 1) focused on geriatric specific syndromes and concepts (e.g., atypical presentation of disease, changes with age, transitions of care) relevant to emergency medicine, 2) focused on clinical issues nearly exclusive to geriatric ED patients (e.g., end of life care, dementia, delirium, systems of care for older adults), or 3) discussing issues common to all ED patients but focused on the unique factors found in older adults (e.g., trauma in older adults, cardiac arrest care for the geriatric patient.) For physician champion / medical directors applying to lead Level 3 Geriatric EDs, 4 hours of education are required for the initial certification and for each renewal. These educational requirements may be demonstrated through appropriate geriatric-focused CME with completion certificate. |  |  | Not Started
Nursing education in geriatric emergency care A department should document its nursing educational activity and submit the documentation for consideration. Some examples: a. GENE course from Emergency Nurses Association https://www.ena.org/education/education/GENE/Pages/default.aspx b. Emergency Department nursing modules from NICHE http://www.nicheprogram.org/knowledgecenter/webinars/archived-webinars/ c. Locally developed nursing education modules |  |  | Not Started
c) Policies/Protocols, Guidelines and Procedures
Provide evidence of at least one geriatric-specific emergency care initiative (e.g. elder mistreatment, cognitive impairment, or other policies/ protocols / procedures.) Protocol should specifically address the emergency care needs of older adults. These protocols or procedures should describe the process through which this care improvement activity takes place for older patients while in the ED and how it is tracked with regards to adherence and care (i.e., who does the process, on whom the process is done, and how the process is triggered, etc.) This description should be detailed enough for the reviewers to understand how it is implemented, including information about staff education, how it is integrated into workflow, and strategies for tracking implementation. These protocols or procedures should describe the process through which a care improvement activity takes place for older patients while in the ED and how it is tracked with regards to adherence and improvement (i.e., who does the process, on whom the process is done, and how the process is triggered, etc.) It is not sufficient to describe an already existent hospital-wide policy that just happens to include the ED or an already existent ED policy that just happens to include older patients. |  |  | Not Started
Provide evidence of a Urinary Catheter Minimization policy/procedure/protocol. ACEP/GEDA believes this policy/procedure/protocol represents standard of care and became baseline for all Geriatric Emergency Departments beginning in 2023. | N/A if Submitting Prior to July, 2023 | N/A if Submitting Prior to July, 2023 | Not Started
Provide evidence of an NPO Status Minimization policy/procedure/protocol. ACEP/GEDA believes this policy/procedure/protocol represents standard of care and became baseline for all Geriatric Emergency Departments beginning in 2023. | N/A if Submitting Prior to July, 2023 | N/A if Submitting Prior to July, 2023 | Not Started
Provide evidence of a Physical Restraint Use policy/procedure/protocol. ACEP/GEDA believes this policy/procedure/protocol represents standard of care and became baseline for all Geriatric Emergency Departments beginning in 2023. | N/A if Submitting Prior to July, 2023 | N/A if Submitting Prior to July, 2023 | Not Started
Documentation of implementation of at least 20 items (prior to July, 2023) or 17 items (if submitting after July, 2023) from the ED Model of Care for patients over 65 yrs These protocols or procedures should describe the process through which this care improvement activity takes place for older patients while in the ED and how it is tracked with regards to adherence and care (i.e., who does the process, on whom the process is done, and how the process is triggered, etc.) A patient’s eligibility for GED initiatives may vary across intervention type and institution. For example, eligibility may be based on age, screening tool results, or prior ED history. While ACEP will accept a range of definitions of patient eligibility, you should specify how you are defining eligibility for the purposes of measuring adherence (i.e., the denominator) for each criterion being evaluated. See https://www.acep.org/globalassets/sites/geda/documnets/edmodelofcarelist.pdf for details about the ED Model of Care. |  |  | Not Started
d) Quality Improvement
Adherence to 3 baseline protocols (urinary catheter minimization, NPO status minimization and physical restraint use) plus 17 components chosen in the Policies, Guidelines and Procedures section based on random chart audit There should be evidence of efforts to ensure effective and appropriate utilization of above policies and guidelines with adherence to the 20 components chosen in “Policies guidelines and procedures”. |  |  | Not Started
e) Outcome Measures
Track at least 3 process and outcome metrics for eligible patients for at least 3 items from the ED Model of Care. See https://www.acep.org/globalassets/sites/geda/documnets/outcomemeasureslist.pdf for details about acceptable measures. The ED should track both process and outcomes metrics related to eligible GED patients. These should include demonstration of process and outcome metrics in the majority of eligible GED patients in at least 3 metrics for at least 3 of the policies/ protocols guidelines or procedures chosen from the ED Model of Care (see Policies/Protocols, Guidelines and Processes section above). |  |  | Not Started
f) Equipment and Supplies
Access to, and pictorial evidence of mobility aids (4-point walkers, canes) for 24/7 use in the ED. |  |  | Not Started
Access to, and pictorial evidence of access to at least 3 additional supplies (see list below) for 24/7 use in the ED. - Non--slip socks - Pressure--ulcer reducing mattresses and pillows - Blanket warmer - Hearing assist devices - Bedside commodes - Condom catheters - Low beds - Reclinable arm chairs |  |  | Not Started
g) Physical Environment
Easy access to, and pictorial evidence of free food and drink, 24 hours a day. |  |  | Not Started
Two chairs per patient bed to promote visitors and the possibility of sitting, and pictorial evidence thereof. |  |  | Not Started
A large-face analog clock in each GED patient room, and pictorial evidence thereof. |  |  | Not Started
Submission of Application for Accreditation
Create a login and complete application via online application portal on the American College of Emergency Physicians' website: https://www.acep.org/geda/ Level 1 applicants will be notified of decision within 16 to 18 weeks after online application is submitted. |  |  | Not Started
Submit application fee of $ 15,000 to the American College of Emergency Physicians via instructions on the ACEP portal. |  |  | Not Started
ACEP will assign a reviewer for a Level 1 site visit. |  |  | Not Started