Key steps to starting a CHW program

| Elements of successful CHW programs |  |
| --- | --- |
| - Leadership buy-in | - Leadership buy-in is essential in supporting any program that carries additional costs to the organization. A CHW program requires an upfront investment and has the potential to help health systems recoup costs in the long run by reducing preventable ED visits and/or readmissions by connection patients to preventive care. |
| - Identify patient population | - Identify the target patient population and define the need to deploy CHWs. |
| - Recruitment | - Identify the target population, based on disease prevalence, barriers to care, patient outcomes, etc. - Develop steps required to recruit a CHW to serve that target population . |
| - Defining the CHW role | - Clearly define the role of the CHW from the perspective of the CHW, health system and community. - Develop a job description for CHW. - Set program goals, which should include identifying the target population, developing a timeline for milestones, and improvement metrics. |
| - Collaboration | - Define how the CHW can collaborate with the patient’s care team. |
| - Training and education | - Develop onboarding and training materials, including any requirements specific to the CHW position. - Include training for health system staff on the role of the CHW and the referral process. |
| - Job essentials | - Determine what equipment and supplies a CHW might need to deliver expected services, both in the office and out in the community. |
| - Supervision | - Establish regular check-ins with CHWs to provide guidance, feedback, case reviews and skill development. |
| - Community involvement | - Define the role of the CHW in the community. - Identify the ways the CHW can be supportive of the population they serve. - Find opportunities for the CHW to attend community events for outreach activities. |
| - Referral Process | - Develop referral criteria, list the markers for a patient to be eligible for CHW support and define the process to document and track referrals. |
| - Documentation and information management | - Determine how the CHW will document progress notes, home visits and services provided. - Set documentation requirements (i.e. notes should be entered within 3 days of service/communication occurring). |
| - Quality checks | - Identify the person who will be responsible for chart reviews for quality purposes. - Determine how to use data from chart reviews to enhance patient care. |
| - Program performance evaluation | - Evaluate program performance against goals and performance indicators regularly |
| - Program budget | - Develop the program budget, which should include personnel costs, equipment/supplies, training and data tracking/management. - Identify internal and/or external funding sources |